## Summary
Version | File name | Description/Comment | Status
0.1 | UMCHANGE-358_XMLTool_Scope_v0.1 | First release: -UMGI/DGP's requirements review and alignment -Status snapshot | In Review - UMGI

## XMLTool_UMGI Scope
Req_ID | Section/Functionality | UMGI Requirements | DGP Solution / Recommendation | Scope | Status
UMGI_01 | Top section | Show BP name | The BP name is already displayed in the tool as "PartyName" | IN | Deployed
UMGI_02 | Top section | Show UPC code | Create a summary section providing an overview of product structure and containing information such as the UPC code, Track listing, Territory listing and Works structure | IN | UMGI to confirm
UMGI_03 | Top section | Show the Date of the message | The Date of the message is already displayed in the tool as "CreationDate". | IN | Deployed
UMGI_04 | Top section | Specify whether the message is an "Update" or a "New" message | Message type is already displayed as part of the "FileName" in the tool | IN | Deployed
UMGI_05 | Resource section | Show the details of all the resources including resource type, title, artists, indirect contributors’ details, durations and technical details. | All the mentioned details are already displayed except the "Duration" which remains to be added | IN | In progress
UMGI_06 | Resource section | This section should consist of collapsible boxes in order to extend or restrict the view of the resources information for each territory at a click of a button. | Resources collapsed by "Resources ID" then by "Territories": - User should click (on "Resources ID" or"Territory") to expand the collapsed details - Color and cursor change when rolling over a "clickable" zone - A link ("See Release") enables the user to display a red frame in the Release section hightlighting related Release informations. | IN | Deployed
UMGI_07 | Resource section | Translation should be included if applicable for Japanese and Chinese | Translation will be displayed when exist for each Resources' Title/Name. E.g: Title: Subtitle : Translated Title (LanguageAndScriptCode) : Translated sub-Title (LanguageAndScriptCode) : Full Name : Key Name : Names after : Translated Name (LanguageAndScriptCode) : Translated Name (LanguageAndScriptCode) : | IN | UMGI to confirm
UMGI_08 | Resourse_Search facility | Ability to search by territory | Create a summary section displaying the list of territories. Give ability to click on a Territory and view Resources informations for each resource for that territory | IN | UMGI to confirm
UMGI_09 | Resourse_Search facility | Ability to search by resource type (Sound Recording, Video, etc) | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_10 | Resourse_Search facility | Ability to search by resource ID (ISRC, ETC) – Search in browser | Create a summary section displaying the track listing. Give ability to click on a Resource ID and view this specific Resource in Resources section | IN | UMGI to confirm
UMGI_11 | Resourse_Search facility | Ability to search the technical details per resource | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_12 | Resourse_Search facility | Ability to search resource reference IDs: Search in browser | Create a summary section displaying the track listing. Give ability to click on a Resource ID and view this specific Resource in Resources section | IN | UMGI to confirm
UMGI_13 | Resourse_Search facility | It should list all resource reference ID and also linking them to their relevant release ID | This requirement is already deployed in the tool. There is a link named "See the release" under each Resource (Resources section) which enable to see the corresponding Release. | IN | Deployed
UMGI_14 | Resourse_Search facility | Ability to search by Artist names and Type (Main artist, Contributors, etc) – Search in browser | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_15 | Release section | Show the details of all the releases | The tool already display all available details on all the existing releases (product and track level) - See Release section | IN | Deployed
UMGI_16 | Release section | This section should consist of collapsible boxes in order to extend or restrict the view of the releases information for each territory at a click of a button. | Releases collapsed by "Release ID" then by "Territories": - User should click (on "Release ID" or"Territory") to expand the collapsed details - Color and cursor change when rolling over a "clickable" zone - A link ("Resource Reference") enables the user to display a red frame in the Resources section hightlighting related Resources informations. - A link ("See the Deal") enables the user to display a red frame in the Deals section hightlighting related deal informations. | IN | Deployed
UMGI_17 | Release section_Search facility | Ability to search by territory | Create a summary section displaying the list of territories. Give ability to click on a Territory and view Releases informations for that territory for each release | IN | UMGI to confirm
UMGI_18 | Release section_Search facility | Ability to search by Release Type | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_19 | Release section_Search facility | Ability to search by Artist name | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_20 | Release section_Search facility | Ability to search by Artist name | Create a summary section displaying the list of Resources Give ability to click on a Resource ID and view Releases informations for that Resource | IN | UMGI to confirm
UMGI_21 | Deal section_Search facility | Ability to search per territory: Show all the various deals for that product per territory | Create a summary section displaying the list of territories. Give ability to click on a Territory and view Deals informations for that territory for each Release | IN | UMGI to confirm
UMGI_22 | Deal section_Search facility | Ability to search per TOU: - Show a specific TOU in all the territory - Treat the Deal cancelled as permissions so show if specific permission are Off ?? | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_23 | Deal section_Search facility | Ability to search by Price code | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_24 | Deal section_Search facility | Ability to search per date range for the various campaigns ?? | Removed from scope. Information are collapsed by Reference IDs then by Territories | OUT | Out of Scope
UMGI_25 | Global searches_Search facility | Ability to search for a specific track should bring back all the details for that single track including, resource, release and deal in collapsible boxes. | Create a summary section displaying the track listing. Give ability to click on a Track's Resource ID or Release ID and view his Resources Releases and Deals informations | IN | UMGI to confirm
UMGI_26 | Global searches_Search facility | Ability to search for a specific territory should bring back all the resources, releases, permissions for that territory in collapsible boxes | Create a summary section displaying the list of territories. Give ability to click on a Territory and view Resources, Releases and Deals informations for that territory for all Resources and Releases | IN | UMGI to confirm

## XML Tool_DGP Scope
Req_ID | Section/Functionality | Internal Requirements | DGP Solution | Scope | Status
DGP_01 | Summary Section | Add UPC, Main artist, title | Create a summary section providing an overview of product structure and containing information such as the UPC code, Main artist, title, Track listing, Territory listing and Works structure | IN | Open
DGP_02 | Summary Section | Add Works structure | Create a summary section providing an overview of product structure and containing information such as the UPC code, Main artist, title, Track listing, Territory listing and Works structure | IN | Open
DGP_03 | Summary Section | Add track listing with all tracks (volume number, track number, ISRC, Main Artist, Title, Resource Reference, Release Reference, Deal Reference, Asset Type (Sound, Video, Image, Booklet)). This could be a hyperlink to move to the relevant section when the user clicks on the track or reference number. | Create a summary section providing an overview of product structure and containing information such as the UPC code, Main artist, title, Track listing, Territory listing and Works structure Give ability to click on a track (Reference ID) and view corresponding Resources, Releases and/or Deal details | IN | Open
DGP_04 | Summary Section | Add territory link to see all territories in the product, and for each track and if possible to click and expand the section for that territory for that track. | Create a summary section providing an overview of product structure and containing information such as the UPC code, Main artist, title, Track listing, Territory listing and Works structure. Give ability to click on a territory and view for each Resources, Release, Deal all details for this territory | IN | Open
DGP_05 | General layout update | Add different colour/underline for expanding sections and cursor change on roll-over. | Sections are collapsed by "Reference ID" then by "Territories": - User should click (on a "Reference ID" or"Territory") to expand the collapsed details - Color and cursor change when rolling over a "clickable" zone | IN | Deployed
DGP_06 | General layout update | Include Digiplug logo | Digiplug's Logo will be displayed in the tool. | IN | In Progress
DGP_07 | Deal Section update | Deals structure to be ordered based on usage same as in the User Interface (Permanent Download, Time Limited, Streaming) - not commercial model. Order: >All Permanent Download >All Time Limited Download >All Streaming | Deals will be displayed in the following order: 1) All Permanent Download 2) All Time Limited Download 3) All Streaming | IN | Open
DGP_08 | Deal Section update | Use the following Deal name format: [Usage] - [Channel type] - [Commercial model] | Deals will be named with the following name format: [Usage] - [Channel type] - [Commercial model] E.g: Permanent Download - FixedLine - Pay As You Go Model | IN | Open
DGP_09 | Deal Section update | Deals section to also show current DSC user interface description of the terms of use - Under DDEX Deal Name and in Parenthesis | Current DSC user interface description of the terms of use will be displayed under DDEX Deal Name and in Parenthesis E.g: Permanent Download - FixedLine - Pay As You Go Model (Permanent Download - Online - A La Carte) | IN | Open
DGP_10 | Resources section layout update | Clearly Separate files' details in the Resources section | File details will be separated with a "carriage return" | IN | Open
DGP_11 | Resources section layout update | Display duration in Sound Recording Section | Linked to UMGI_05 | IN | Duplicate
DGP_12 | Translations | Take into account Translations when exist | Linked to UMGI_07 | IN | Duplicate