## XMLTool_Scope
Section/Functionality | Requirements | Scope | AB-28319 Sub task | Status | Comment
Top section | Header information: | IN |  | Live
Top section | BP name | IN |  | Live | PartyName
Top section | UPC code | IN | AB-28329 | To be Confirmed | UPC is mentionned In FileName Do we need a separate label "UPC Code"
Top section | Date of the message | IN |  | Live | CreationDate
Top section | Update or New message: | IN |  | Live | In FileName
Resource section | Show the details of all the resources including resource type, title, artists, indirect contributors’ details, durations and technical details. | IN | AB-28331 | Partially Live | Duration remain to be added
Resource section | This section should consist of collapsible boxes in order to extend or restrict the view of the resources information for each territory at a click of a button. | IN | AB-28333 | Live
Resource section | Translation should be included if applicable for Japanese and Chinese | IN | AB-28332 | Planned | Workaround: Link in summary section to Resouce section Should we anticipate iTunes localization?
Resourse_Search facility | Search by territory – Link to display language information for product / component? | IN | AB-28329 | Planned | Workaround: Link in summary section to Resouce section
Resourse_Search facility | Search by resource type (Sound Recording, Video, etc) – Why? | TBC |  | N/A
Resourse_Search facility | Search by resource ID (ISRC, ETC) – Search in browser | IN | AB-28329 | Planned | Workaround: Link in summary section to Resouce section
Resourse_Search facility | Search the technical details per resource ?? | IN | AB-28329 | Planned | Workaround: Link in summary section to Resouce section
Resourse_Search facility | Search resource reference IDs: Search in browser | IN | AB-28329 | Planned | Workaround: Link in summary section to Resouce section
Resourse_Search facility | It should list all resource reference ID and also linking them to their relevant release ID | IN | AB-28329 | Planned | Workaround: Link in summary section to Resouce section
Resourse_Search facility | Search by Artist names and Type (Main artist, Contributors, etc) – Search in browser | TBC |  | N/A
Release section | Show the details of all the releases ?? | IN |  | Live
Release section | This section should consist of collapsible boxes in order to extend or restrict the view of the releases information for each territory at a click of a button. | IN | AB-28333 | Live
Release section_Search facility | Search by territory | IN | AB-28329 | Planned | Workaround: Link in summary section to Release section
Release section_Search facility | Search by Release Type |  | AB-28330 | Planned | Workaround: Link in summary section to Release section
Release section_Search facility | Search by Artist name | TBC |  | N/A
Release section_Search facility | Search by resource reference ID | IN | AB-28330 | Partially Live | Workaround: Link in summary section to Release section (to do) Workaround: Link on top of release section to diffrent release (live)
Deal section_Search facility | Search per territory: Show all the various deals for that product per territory | IN | AB-28329 | Planned | Workaround: Link in summary section to Deal section
Deal section_Search facility | Search per TOU: - Show a specific TOU in all the territory - Treat the Deal cancelled as permissions so show if specific permission are Off ?? | TBC |  | N/A
Deal section_Search facility | Search by Price code | TBC |  | N/A
Deal section_Search facility | Search per date range for the various campaigns ?? | TBC |  | N/A
Global searches_Search facility | A search for a specific track should bring back all the details for that single track including, resource, release and deal in collapsible boxes. | IN | AB-28329 | Planned | Workaround: Link in summary section to Resource, Release and Deal sections
Global searches_Search facility | A search for a specific territory should bring back all the resources, releases, permissions for that territory in collapsible boxes | TBC |  | N/A